## MVP Tracker
Functional Area | Feature / Requirement | Assignee | Status | Evidence
Login & User Access | User authentication |  | Not Started | admin-users.png
| Access control |  | Not Started | admin-users.png
| Role-based permissions |  | In Progress | admin-roles.png
Project Management | Create, edit, and delete projects |  | Completed | admin-projects.png
| Demo project creation |  | Completed | project-switcher-open.png
| Multi-project support |  | Completed | project-switcher-open.png
| Project switching |  | Completed | project-switcher-open.png
| Project-level settings |  | In Progress | settings.png
Test Case Management | Create test cases |  | Completed | create-testcase-modal.png
| Edit test cases |  | Completed | testcase-detail-panel.png
| Bulk edit test cases |  | Not Started | testcase-bulk-select.png
| Duplicate/delete test cases |  | Completed | testcase-row-menu.png
| Test case ownership |  | Completed | testcase-detail-panel.png
| Test case templates — Steps |  | Completed | testrun-case-execution.png
| Test case templates — Text |  | Completed | testcase-detail-panel.png
| Preconditions |  | Completed | testcase-detail-panel.png
| Expected results |  | Completed | testcase-detail-panel.png
| Rich text editing |  | Not Started | testcase-detail-panel.png
| Attachments and images |  | In Progress | testcase-detail-panel.png
| Test case versioning/history |  | In Progress | testcase-history-tab.png | *
| Test case organization |  | Completed | testcases.png | *
Test Case Organization | Folder management |  | In Progress | testcases.png
| Subfolder management |  | In Progress | testcases.png
| Drag-and-drop organization |  | Not Started | testcases.png
| Test case ordering |  | Not Started | testcases.png
| Move/copy test cases |  | Not Started | testcase-row-menu.png
| Move/copy folders |  | Not Started | testcases.png
| Cross-project test case movement |  | Not Started | testcases.png
Test Planning | Create test plans |  | Completed | plans.png
| Edit test plans |  | Completed | plan-detail.png
| Duplicate test plans |  | Completed | plan-more-menu.png
| Delete test plans |  | Completed | plan-more-menu.png
| Static test selection |  | Completed | plan-testcases-tab.png
| Dynamic test selection |  | Completed | plan-testcases-tab.png
| Folder-based queries |  | Completed | plan-testcases-tab.png
| Condition-based queries |  | Completed | plan-testcases-tab.png
| Test plan coverage management |  | Completed | plan-detail.png
Test Run Management | Create test runs |  | Completed | dashboard.png
| Create runs from test plans |  | Completed | plan-detail.png
| Manual run creation |  | Completed | testruns.png
| Run assignment |  | Completed | testruns.png
| Run scheduling |  | Not Started | testruns.png
| Run status tracking |  | Completed | testruns.png
| Run filtering |  | Completed | testruns.png
| Open/closed runs |  | Completed | testrun-more-menu.png
Test Execution | Execute test cases |  | Completed | testrun-case-execution.png | ?
| Execute test runs |  | Completed | testruns.png
| Record test results |  | Completed | testrun-case-execution.png
| Step-by-step execution |  | Completed | testrun-case-execution.png
| Pass/Fail/Blocked tracking |  | Completed | testrun-case-execution.png
| Tester assignment |  | Completed | testruns.png
| Execution progress monitoring |  | Completed | testruns.png
| Personal work queues |  | Not Started | testruns.png
Re-Run Management | Create re-runs |  | Not Started | testrun-more-menu.png
| Failed test re-execution |  | Not Started | testrun-more-menu.png
| Blocked test re-execution |  | Not Started | testrun-more-menu.png
| Selective regression execution |  | Not Started | testrun-more-menu.png
Requirements Management | Requirement creation |  | Completed | testcase-requirements-tab.png
| Requirement linking |  | Completed | testcase-requirements-tab.png
| Requirement traceability |  | In Progress | run-case-requirements-tab.png | *
| Requirement coverage tracking |  | Not Started | testcase-requirements-tab.png
| Integration-based requirement synchronization |  | Not Started | testcase-requirements-tab.png | ?
Defect Management | Defect creation |  | Completed | defects.png
| Defect linking |  | Completed | defects.png
| Defect tracking from test execution |  | Completed | testrun-case-execution.png
| Defect traceability |  | Completed | defects.png | *
| Defect integration with external tools |  | Not Started | defects.png
Reporting & Analytics | Test run summary reports |  | In Progress | dashboard.png
| Historical analysis |  | In Progress | dashboard.png
| Test plan analytics |  | In Progress | plan-detail.png
| Failure trend analysis |  | Not Started | dashboard.png
| Coverage metrics |  | In Progress | dashboard.png
| Execution metrics |  | In Progress | dashboard.png
| Dashboard reporting |  | Not Started | dashboard.png
| Test effectiveness analysis |  | Not Started | dashboard.png
Export & Reporting | PDF report generation |  | In Progress | export-button-click.png
| Excel export |  | In Progress | run-export-menu.png
| CSV export |  | In Progress | run-export-menu.png
| Archived test results |  | Not Started | testruns.png
| Shareable reports |  | Not Started | reports.png
User & Role Management | User invitations |  | Completed | admin-users.png
| User removal |  | Not Started | admin-users.png
| Role assignment |  | Completed | admin-users.png
| Permission management |  | In Progress | admin-roles.png
Search, Filter & Query Management | Test case filtering |  | Completed | testcases-filter-panel.png
| Test run filtering |  | Completed | testruns.png
| Dynamic queries |  | Completed | plan-testcases-tab.png
| Saved conditions |  | Not Started | testcases-filter-panel.png
| Table filtering |  | Completed | testcases.png
| Search capabilities |  | In Progress | search-cmd-k.png
Audit History / Versioning | Audit trail |  | In Progress | audit.png
| Change history |  | In Progress | testcase-history-tab.png
| Version management |  | Not Started | testcase-history-tab.png